## Sprint Metrics
Sprint | Planned SP | Completed SP | Carry Forward | Production Defects | UAT Defects | Team Size | Velocity | Sprint Goal
S1 | 80 | 75 | 5 | 2 | 6 | 8 | 75 | Customer Onboarding
S2 | 90 | 84 | 6 | 1 | 5 | 8 | 84 | Card Issuing
S3 | 100 | 96 | 4 | 2 | 2 | 9 | 96 | Transactions API
S4 | 110 | 88 | 22 | 5 | 12 | 9 | 88 | Fraud Engine
S5 | 120 | 115 | 5 | 1 | 3 | 10 | 115 | Reporting
S6 | 130 | 118 | 12 | 3 | 7 | 10 | 118 | Performance Tuning
S7 | 140 | 132 | 8 | 1 | 4 | 11 | 132 | Security Hardening
S8 | 150 | 121 | 29 | 6 | 11 | 9 | 121 | UAT Closure

## Budget
Month | Planned($) | Actual($)
Jan | 50000 | 52000
Feb | 60000 | 58000
Mar | 65000 | 72000
Apr | 70000 | 76000