# Contoso Bank Modernization - Steering Committee Meeting Transcript

Date: 05-Oct-2026
Attendees: Program Manager, Architect, Security Lead, Dev Lead, QA Lead.

Discussion Points:
1. Sprint 8 closed at 81% velocity versus planned target.
2. Fraud Engine service caused 6 production incidents due to timeout issues.
3. Security assessment identified 3 High and 7 Medium vulnerabilities.
4. UAT completion is at 78%; Payments and Reporting modules still pending sign-off.
5. Azure AKS cluster costs exceeded budget by 12% due to over-provisioned nodes.
6. Customer onboarding microservice achieved response time target of <200ms.
7. Release readiness score assessed at 72/100.

Decisions:
- Production release moved from 20-Oct to 27-Oct contingent on security closure.
- Additional performance test cycle approved.

Actions:
Ravi: Resolve AKS scaling issue by 10-Oct.
Nisha: Close High vulnerabilities by 15-Oct.
Ajay: Execute performance benchmark testing.
Meena: Obtain UAT sign-off from business stakeholders.

Risks:
- Security vulnerabilities delaying release.
- Budget overrun may exceed forecast by 8%.
- Fraud API instability could impact production readiness.

Open Questions:
- Whether multi-region deployment is required for Phase 1.
- Whether partner API certification can be completed before go-live.